Project Management Plan and Risk Assessment

24 October 2026

Project: Development of a Web Application for Enhancing Digital Skills of Older Adults

Team: Symbat Zhuman and Gulnaz Nurseit

Supervisor: Aliya Katyetova

1. Purpose and Project Scope

This plan explains how our two-person team organizes the diploma project, shares responsibilities, checks progress, and manages risks. The application is intended for adults aged 50 and above. It will support initial skills assessment, learning lessons, interactive exercises, basic personalized recommendations, and progress tracking. The planned technology stack is Angular and TypeScript for the frontend, Node.js and Express for the backend, and PostgreSQL for data storage

2. Team Responsibilities

| Team member | Main responsibilities | Expected outputs |
| --- | --- | --- |
| Symbat Zhuman | Frontend development using Angular and TypeScript; UX prototype; readable and accessible interface; responsive pages; frontend API integration; interface testing. | UI/UX designs, learner-facing screens, frontend components, accessibility checks. |
| Gulnaz Nurseit | Backend development using Node.js and Express; PostgreSQL database; authentication; assessment logic; learning content APIs; recommendations and progress records; API testing. | Backend services, database schema, REST APIs, progress and recommendation logic. |
| Both members | Requirements review, user research, architecture discussions, integration, testing, GitHub code review, and supervisor communication. | Reviewed project documents, integrated application, testing evidence. |

The division of work follows the selected technology stack. Symbat mainly develops the learner-facing interface and checks that the screens are easy to read and navigate. Gulnaz mainly develops the server-side logic, APIs, and database. This division allows both members to focus on their main technical areas.

Some activities require joint work. For example, the frontend needs API responses from the backend, so both members must agree on request formats and data fields. Requirements, testing results, and important design changes should also be reviewed together. If one member is unavailable, the other member can help with documentation and review, but major technical changes should be discussed first.

3. Timeline and Milestones

The first preparation stage has a deadline of 24 October 2026. Dates for later diploma stages are marked TBC (To Be Confirmed). This means the exact deadline has not yet been approved and will be agreed with the supervisor. The milestones follow the order described in the official project justification.

| Stage | Target date | Main deliverables |
| --- | --- | --- |
| 1. Research and planning | 17–24 Oct 2026 | Project proposal, interviews, literature review, article analysis, comparisons, SRS, diagrams, UX prototype, verification plan, and project management plan. |
| 2. Architecture and detailed design | TBC | Reviewed architecture, database design, API plan, updated UX screens. |
| 3. Frontend and backend development | TBC | Angular interface, Express APIs, PostgreSQL database, learning and assessment features. |
| 4. Integration and testing | TBC | Integrated features, functional and accessibility tests, fixed issues. |
| 5. Final documentation and defense | TBC | Final report, presentation, completed application, and defense materials |

The first milestone focuses on preparing the project before implementation. Its outputs provide evidence of user needs, explain the choice of technologies, and describe the planned system. The architecture and UX materials from this stage can be improved during detailed design when new information becomes available.

During development, the team will first prepare the database and main API endpoints, then connect them to the Angular interface. The main features will include account access, an initial skills assessment, learning content, exercises, basic rule-based recommendations, and progress tracking. Integration and testing will follow in small parts instead of waiting until the entire application is finished.

Each milestone is complete when its expected deliverables have been reviewed and stored in the repository. The exact dates of stages 2–5 remain TBC until the team receives the official schedule. The team will update this table if the supervisor changes the project scope or deadlines.

4. YouTrack Task Plan

YouTrack is used to assign work, set deadlines, record acceptance criteria, and track progress. The table presents the agreed reporting view for 24 October 2026: DSOA-1 to DSOA-11 are treated as completed, DSOA-12 is in progress, and DSOA-13 is planned next. The team must update the live YouTrack statuses to match the actual completed work before submission.

| ID | Task | Owner | Due | Priority | Status |
| --- | --- | --- | --- | --- | --- |
| DSOA-1 | Project proposal | Symbat | 17 Oct | Normal | Done |
| DSOA-2 | Project relevance interviews | Gulnaz | 24 Oct | Major | Done |
| DSOA-3 | Literature review | Gulnaz | 21 Oct | Major | Done |
| DSOA-4 | Analysis of 10 research articles | Symbat | 22 Oct | Major | Done |
| DSOA-5 | Existing platform comparison | Symbat | 19 Oct | Normal | Done |
| DSOA-6 | Technology comparison | Gulnaz | 22 Oct | Major | Done |
| DSOA-7 | Functional and non-functional requirements | Gulnaz | 23 Oct | Major | Done |
| DSOA-8 | System context and use case diagrams | Symbat | 23 Oct | Normal | Done |
| DSOA-9 | Component diagram and architecture | Gulnaz | 24 Oct | Normal | Done |
| DSOA-10 | Accessible UX prototype | Symbat | 23 Oct | Normal | Done |
| DSOA-11 | Verification and evaluation plan | Gulnaz | 24 Oct | Major | Done |
| DSOA-12 | Management plan and risks | Symbat | 24 Oct | Normal | In progress |
| DSOA-13 | Supervisor feedback documentation | Gulnaz | 24 Oct | Major | To do |

The task table makes responsibilities and deadlines visible to both members. The due dates refer to the first project stage in October 2026. Priority describes the importance of a task for project planning; it does not show whether the task has been completed. Major tasks require particular attention, while Normal tasks remain part of the required project work.

For each YouTrack issue, the team checks the acceptance criteria before closing it. For example, DSOA-8 requires editable diagrams and exported images, DSOA-10 requires an editable UX prototype with clear navigation, and DSOA-12 requires this management plan, task dependencies, and a risk table. A task should be marked Done only when the required files and review are complete.

The task owner is responsible for preparing the deliverable and updating YouTrack. The other member reviews the result in GitHub. This process helps the team identify missing files, incorrect links, or differences between the documentation and the current project requirements.

5. GitHub Structure and Collaboration Rules

Repository: https://github.com/symbat27/digital-skills-older-adults

YouTrack project: https://digital-skills-older-adults.youtrack.cloud/projects/DSOA

We keep project documents in the docs/ directory, including research, requirements, diagrams, and prototype materials. New management documents will be stored in docs/management/. Source code will be organized into frontend and backend folders when implementation begins.

For each task, we create a branch from main using its issue ID (for example, DSOA-12). Commits describe the change, such as “DSOA-12: add project management plan”. We open a pull request to main, link the related YouTrack issue, and ask the other team member to review it. We address comments before merging. Important changes should not be made directly on main.

The assignee updates the YouTrack status and due date when needed. A task is marked Done after its deliverables meet the acceptance criteria and the related changes have been reviewed.

The repository separates documents by purpose. Research materials are stored under docs/research/, requirements under docs/requirements/, and system diagrams under docs/diagrams/. UX prototype files and exports are kept with the project documentation. The management plan belongs in docs/management/. This structure makes it easier to find the latest version of each deliverable.

The team will avoid uploading passwords, private participant details, or other sensitive information. If two members edit related files, they should coordinate before merging to reduce conflicts. The latest approved documents in main will be treated as the shared project version.

6. Task Dependencies

| Dependency | Reason |
| --- | --- |
| DSOA-2, 3, 4, 5 → DSOA-7 | User evidence and background research help define realistic requirements. |
| DSOA-6, 7 → DSOA-9 | Architecture should follow the technology choice and system requirements. |
| DSOA-7, 8 → DSOA-10 | The prototype should match functional requirements and user scenarios. |
| DSOA-7, 9, 10 → DSOA-11 | The evaluation plan should cover requirements, components, and UX flows. |
| Design and backend APIs → integration | Frontend and backend must agree on data formats and endpoints. |
| Integration → testing → final report | The final results depend on a working and tested application. |

These dependencies show the recommended order of work, not a rule that all tasks must be completed one after another. Research and user discussions help the team understand real learning needs before finalizing requirements. The SRS then guides the system diagrams, architecture, and UX prototype.

Architecture and UX design can continue in parallel after the main requirements are agreed. However, frontend and backend integration depends on common API definitions. The evaluation plan should use the requirements and prototype as a basis for test cases. If an earlier decision changes, the team will review the affected tasks and update related documents.

7. Risk Assessment

Likelihood describes how likely a problem is to happen. Impact describes how strongly it could affect the project. Both are rated Low, Medium, or High. These are the team’s planning estimates, not measured probabilities. The mitigation column explains how the team can prevent the problem or reduce its effects.

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Limited participation in user interviews | Medium | High | Recruit participants early; use short questions; document consent and anonymous findings. |
| Accessibility problems for adults 50+ | Medium | High | Review text size, contrast, navigation, and instructions; test with target users. |
| Frontend and backend integration delays | Medium | High | Agree on API contracts early; integrate small features regularly. |
| Tasks completed close to deadlines | High | Medium | Break work into smaller tasks; check YouTrack regularly; review progress together. |
| Database or authentication errors | Medium | High | Use validation, tests, backups, and careful access controls. |
| Personalization does not match user needs | Medium | Medium | Start with simple rule-based recommendations and validate against requirements. |
| Git merge conflicts or missing files | Medium | Medium | Use separate branches, frequent commits, pull requests, and peer reviews. |
| Changes requested by supervisor | Medium | Medium | Keep time for revisions and document feedback in YouTrack. |

The most important technical risks are accessibility problems and delays when connecting frontend and backend components. To reduce accessibility problems, the team will use readable text, clear buttons, consistent navigation, and understandable instructions, and later check the interface with target users aged 50+. For integration, the team will agree on API formats early and test small features regularly.

Project management risks are also important because the team has only two members and several tasks share the same deadline. Short progress checks, early reviews, and clear ownership can reduce last-minute work. The risk table will be updated when new problems appear, when a mitigation action is completed, or when the supervisor gives new instructions.

8. Team Review and Communication

The team will discuss task progress, blockers, and upcoming deadlines during regular short check-ins. GitHub pull requests will be used to review files and code, while YouTrack will record the owner, due date, and current state of each task. Important decisions should be written down so that both members can follow the same plan.

Before the management plan is considered complete, Symbat and Gulnaz should confirm the responsibility table, milestones, dependencies, and risk ratings. Any changes requested during review should be included in the next saved version. Supervisor feedback will be documented through DSOA-13 and may lead to updates in this plan.

9. Conclusion

This management plan gives our team a clear way to organize the diploma project. It defines responsibilities, milestones, collaboration rules, dependencies, and project risks. Following this plan will help us complete the application step by step and keep our work consistent with the requirements.